## Project schedule
| CIVE 202 Project #3 | Project Members |  |  |  |  | Project start: | [7 empty] | 2026-02-26 | [9 empty] | Project start: | [7 empty] | 2026-03-31
| VISUALIZE | Michael McCarthy |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-23 to 2026-04-19
 | time axis 2026-02-23 to 2026-04-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning for function development
| Task Project Planning (Gantt Chart) | Michael McCarthy | 100% | 2026-02-26 | 2026-02-26 | 1
| Task #1 Research / Define categories for Bar chart visualisation | Michael McCarthy | 100% | 2026-02-27 | 2026-02-28
| Task #1 Research / Define categories for Histogram visualisation | Michael McCarthy | 100% | 2026-03-01 | 2026-03-02
| Task #1 Research/ Define categories for boxplot visualisation | Michael McCarthy | 100% | 2026-03-03 | 2026-03-04
| Task #1 Research / Define categories time-series plot categories | Michael McCarthy | 100% | 2026-03-05 | 2026-03-06
| Task #2 Research / Define and define variables for analysis in IDM sim | Michael McCarthy | 100% | 2026-03-07 | 2026-03-11 | 5
Draft functions in Python
| Task #1 Programming for Bar chart visualisation | Michael McCarthy | 100% | 2026-03-06 | 2026-03-07 | 2
| Task #1 Programming for Histogram visualisation | Michael McCarthy | 100% | 2026-03-08 | 2026-03-09 | 2
| Task #1 Programming for boxplot visualisation | Michael McCarthy | 100% | 2026-03-10 | 2026-03-11 | 2
| Task #1 Programming for time-series plot categories | Michael McCarthy | 100% | 2026-03-12 | 2026-03-13
| Task #2 IDM sim | Michael McCarthy | 100% | 2026-03-14 | 2026-03-19
Execution
| Data cleaning and Processing | Michael McCarthy | 80% | 2026-03-20 | 2026-03-21
| Testing and validation | Michael McCarthy | 90% | 2026-03-22 | 2026-03-23
| Written Technical Report | Michael McCarthy | 100% | 2026-03-24 | 2026-03-27
| Annotated Code Document (ACD) | Michael McCarthy | 0% | 2026-03-06 | 2026-03-19
| Scope of Work (SOW) | Michael McCarthy | 100% | 2026-03-01 | 2026-03-06
| Final Project integration and submission | Michael McCarthy | 0% | 2026-03-29 | 2026-03-31
Evaluation
| Monitor progress | Michael McCarthy | 80% | 2026-02-26 | 2026-03-30 | 33
| Task #3 Track Billable Hours | Michael McCarthy | 90% | 2026-02-26 | 2026-03-30
| Evaluate progress | Michael McCarthy | 80% | 2026-03-06 | 2026-03-30 | 25
| Gather feedback | Michael McCarthy | 0% | 2026-03-31 | 2026-04-05 | 6
Formulas:
Display week: = [Display week:, row below]